Women-Led Smallholder Farm Mechanization for Sustainable Livelihoods

Proposal Prepare by: WOGEN CHILDREN AND MOTHERS SUPPORT ASSOCIATION-SEATTLE CHAPTER

September 2026

Contents

Executive Summary	3

1.	Project Profile	4

2.	Wogen Children and Mothers Support Association Organizational Profile	4

3.	The Development Problem	5

4.	Goal and Specific Objectives	6

5.	Project Targets	6

6.	Major Project Activities and Immediate Outputs	6

7.	Expected Outcomes	7

8.	Expected Economic and Social Gains	7

9.	Theory of Change	10

10.	Business and Service Delivery Model	10

11.	Mechanization Service	11

12.	Appropriateness of Power Tillers for Smallholder Farmers	11

13.	Project Investment and Cost Structure	14

14.	Community Contribution and Cost Sharing	14

15.	Operating and Maintenance Responsibility	14

16.	Sustainability and Exit Strategy	15

17.	Procurement, Transport and Commissioning	15

18.	Governance and Institutional Arrangements	16

19.	Gender and Inclusion Strategy	16

20.	Implementation Schedule	17

21.	Results Framework	18

22.	Monitoring and Learning	18

23.	Key Risks and Mitigation	18

# Executive Summary

This four-year project will establish a practical, community-managed farm mechanization service in Chilga, Lay Armachiho and East Dembia Woredas (Districts) of Central Gondar Zone, Amhara Region. The project will introduce 15 power tillers (five in each woreda) to organized groups of smallholder farmers who live in close proximity and can cluster their land for efficient and timely use of the machinery. The intervention is designed to improve access to farm power, reduce dependence on labour- and ox-drawn land preparation, and strengthen the capacity of smallholder farmers to manage and sustain mechanization services collectively. The project will prioritize women-headed households, with 60% of participating farmers being women-headed households and 40% men. Target farmers are expected to cultivate approximately 1.5-2.5 hectares and will be organized into user groups based on geographical proximity and shared demand for mechanization services. Each power tiller is expected to serve approximately 15-20 organized farmer groups/users, resulting in estimated 225-300 smallholder participants across the three woredas.

The project will use a shared-responsibility and community ownership model. The assumed cost of one power tiller is ETB 200,000. The community will contribute 10% (ETB 20,000) per machine, while the project will finance the remaining 90% (ETB 180,000). Participating farmers will assume responsibility for fuel, operator/labour costs, routine servicing, repairs, maintenance and other recurrent operating expenses. This arrangement is intended to create a meaningful community ownership commitment, promote responsible use of the machinery, and reduce dependence on continued donor financing. Wogen Children and Mothers Support Association- Seattle Chapter will serve primarily as a facilitator, capacity builder and monitor, rather than as the permanent operator of the machines. Its role will progressively decline as user groups develop the capacity to independently manage the mechanization service.

The four-year implementation period will, therefore, follow a progressive pathway: Year 1-establish and organize; Year 2-consolidate service delivery and management; Year 3- strengthen utilization, cost recovery and local capacity; and Year 4- institutionalize the system, assess sustainability and progressively exit. By the end of the project, user groups are expected to assume full responsibility for machine operation, maintenance, scheduling, financial management and accountability, leaving behind a locally managed mechanization service capable of continuing beyond external project support.

The project is expected to commence between January and mid-March 2027, subject to funding, procurement and implementation arrangements.

# Project Profile

| Project element | Description |
| --- | --- |
| Project title | Women-Led Smallholder Farm Mechanization for Sustainable Livelihoods |
| Purpose | To improve smallholder farmers’ access to affordable and timely farm mechanization, increase agricultural productivity and incomes, and reduce the labour burden associated with land preparation. |
| Implementing organization | Wogen Children and Mothers Support Association- Seattle Chapter |
| Project duration | 4 years |
| Project areas | Chilga, Lay Armachiho and East Dembia Woredas (districts), Central Gondar Zone, Amhara Region |
| Target smallholders | 225-300 participant individual farmers |
| Gender focus | 60% women-headed households and 40% men headed household |
| Typical landholding | 1.5-2.5 hectares per participating smallholder |
| Power tillers | 15 power tillers (5 per woreda) |
| User organization | Geographically clustered farmers organized into user groups to facilitate collective access to machinery and coordinated land preparation. |
| Estimated machine cost | ETB 200,000 per power tiller |
| Total equipment acquisition cost | ETB 3,000,000 for 15 power tillers |
| Community/users contribution | 10% of machine cost = ETB 300,000 |
| Project contribution to equipment | 90% = ETB 2,700,000 |
| Other project costs | Transport, delivery, commissioning, initial technical training and related start-up costs to be determined through quotations. |
| Operating-cost principle | Users cover fuel, operator/labour, routine maintenance, repairs, lubricants and other operating costs. |
| Planning currency | Ethiopian Birr (ETB) |
| Expected project start | January-mid-March 2027, subject to funding, procurement and implementation arrangements. |

# Wogen Children and Mothers Support Association Organizational Profile

Wogen Children and Mothers Support Association-Seattle Chapter is a nonprofit organization incorporated in the State of Washington, USA (UBI No. 603101757), working to improve the well-being and self-reliance of vulnerable children, mothers, youth, and underserved communities. Its mission focuses on promoting access to safe water, sanitation, healthcare and education, while increasingly supporting youth and mothers through empowerment and livelihood-oriented initiatives.

The organization’s development approach emphasizes community participation, empowerment, transparency and sustainable solutions. Rather than focusing only on immediate assistance, the organization seeks to strengthen communities' capacity to address their own needs and sustain project benefits. Its stated vision is to contribute to community self-reliance and progress toward meeting basic needs.  The organization has experience supporting community initiatives in water and sanitation, education, health, food assistance, youth empowerment and community development. Its documented activities include supporting water infrastructure in communities and schools, providing educational resources, facilitating community peace and stability initiatives, and supporting vulnerable students.

Wogen has also begun implementing economic empowerment initiatives. In one initiative operating across five towns, selected mothers and youth were supported to establish small businesses through an interest-free revolving fund. Participants receive start-up financing, repay the funds over an agreed period, and repayments are intended to support subsequent beneficiaries. The organization's core values include equality and non-discrimination, transparency, accountability and community empowerment. Wogen states that it does not discriminate on the basis of gender, race, religion, political belief or national origin and that resources are intended to be directed toward its programs rather than private benefit.

# The Development Problem

Many smallholders have land but face difficulty obtaining timely farm traction. Reliance on oxen becomes especially difficult when households do not own enough oxen, services are scarce, or land preparation must be completed within a short agricultural window. Delayed land preparation can lead to late planting, lower productivity and underuse of available land.

Women-headed households are a priority because they may face greater difficulty accessing productive assets and farm traction. A machine given to an individual farmer is also unlikely to be used efficiently on small and scattered plots. A clustered service model allows nearby farmers to share one machine and organize land preparation in sequence.

# Goal and Specific Objectives

Goal: To improve the productivity, income and resilience of smallholder farming households by expanding affordable and timely access to community-managed farm mechanization, with priority given to women-headed households.

- Provide 15 appropriate power tillers-five in each target woreda-to organized farmer groups.

- Enable 225-300 smallholders to access timely land-preparation and related mechanization services.

- Ensure at least 60% of participating beneficiaries are women-headed households.

- Reduce delays and transaction costs associated with land preparation for farmers with 1.5-2.5 hectares.

- Establish a user-financed system covering fuel, operator/labour, servicing and repairs.

- Build local capacity to operate, manage and maintain the machines safely and efficiently.

# Project Targets

| Parameter | Target |
| --- | --- |
| Target woredas | Chilga, Lay Armachiho and East Dembia |
| Power tillers | 15 total (5 per woreda) |
| Expected users/groups per machine | 15-20 |
| Estimated smallholder beneficiaries | 225-300 |
| Women-headed households | 60% |
| Men headed household | 40% |
| Expected landholding | 1.5-2.5 hectares per farmer |
| Project period | 4 years |

Farmers will be selected based on active farming, land possession, need for mechanization, and geographical proximity to other users, willingness to cluster land and follow a common schedule, and willingness to contribute 10% of the machine cost and pay all operating costs.

# Major Project Activities and Immediate Outputs

| Major activity | Expected output |
| --- | --- |
| Community mobilization and beneficiary selection | Transparent selection of 225-300 participating smallholders, with priority to women-headed households |
| Farmer/user-group formation | Organized farmer groups established around geographically clustered farms |
| Land clustering and mechanization planning | Farmers coordinate their plots to facilitate efficient machine utilization |
| Procurement of 15 power tillers | 15 appropriate and locally serviceable power tillers procured |
| Transport and delivery | Machines safely transported and delivered to the three project woredas |
| Commissioning and technical orientation | Machines tested, commissioned and formally handed over to organized users |
| Operator and user training | Local operators and farmer groups trained in safe operation, basic care and routine maintenance |
| Mechanized land preparation | Farmers gain timely access to power-tiller services for land preparation |
| User payment and cost-recovery system | Operating costs covered by users through agreed service payments |
| Monitoring and technical support | Machine utilization, farmer participation, gender inclusion, costs and results monitored throughout the project |

# Expected Outcomes

225–300 smallholders gain reliable access to farm mechanization.

- At least 60% of participating households are women-headed households.

- Farmers with 1.5-2.5 hectares prepare land more timely and efficiently.

- Dependence on scarce or expensive ox-ploughing arrangements is reduced.

- Fifteen community-managed machines remain operational through user-funded operation and maintenance.

- Local operators and farmer leaders gain practical machinery-management skills.

- Evidence is generated for replication in similar smallholder farming areas.

# Expected Economic and Social Gains

i. Economic impacts

The project is expected to:

- Reduce the cost and time of land preparation compared with reliance on manual labour.

- Enable farmers to undertake land preparation more timely, which can contribute to better crop establishment and productivity.

- Increase the effective use of farmers' 1.5-2.5 hectare holdings.

- Reduce farmers' dependence on expensive or unavailable conventional tractor services.

- Generate local employment and income opportunities for trained machine operators.

- Create a locally managed mechanization service business model that can continue beyond donor support.

- Enable participating groups to generate sufficient user revenue to finance fuel, maintenance and repairs.

- Improve household income by reducing production costs and potentially increasing agricultural output.

ii. Social impacts

The project is expected to:

- Reduce the heavy physical burden of land preparation, particularly for women-headed households.

- Increase women's participation in productive agricultural decision-making.

- Strengthen cooperation among farmers through collective land-use and machinery-user groups.

- Improve access to productive assets for smallholders who otherwise have limited access to mechanization.

- Strengthen local institutions for collective economic action.

- Build farmers' confidence and capacity to manage productive assets collectively.

iii. Technology impacts

The project will introduce appropriate small-scale mechanization that is more compatible with relatively small and clustered holdings than large-scale agricultural machinery.

Expected technological gains include:

- Increased farmer exposure to mechanized agriculture.

- Development of local operator skills.

- Improved knowledge of machinery operation and preventive maintenance.

- Establishment of local arrangements for spare parts, repairs and servicing.

- Demonstration of a smallholder-oriented mechanization model that could potentially be replicated in other areas.

iv. Institutional and organizational impacts

The project should also leave behind an institutional asset, not simply machines. So the instiution to be established depicts in the diagram below:

This creates a practical system for managing the machines, collecting user payments, maintaining equipment and making decisions about their use.

v. Overall Expected Impact

Organized farmer/user groups Investment in 15 power tillers Timely and affordable mechanized land preparation Lower labour burden and production costs Improved timeliness/productivity of farming Higher and more reliable farm income Greater economic participation of women and smallholders A sustainable, locally managed farm-mechanization model

# Theory of Change

| Level | Statement | Key assumptions |
| --- | --- | --- |
| Inputs | 15 power tillers and implements, training, governance support, M&E and initial project support | Machines are technically appropriate; parts and technical support are available |
| Activities | Selection, geographical clustering, training, land preparation, scheduling, bookkeeping, maintenance and controlled external hire where appropriate | Members cooperate; operators perform reliably; seasonal demand exists |
| Outputs | 225-300 smallholders organized; 15 machines operational; hectares serviced; records maintained | Adequate machine uptime and user participation |
| Outcomes | Timely cultivation, controlled traction costs, stronger shared-service enterprises and greater women's participation | Weather and input constraints do not overwhelm benefits |
| Impact | Improved farm productivity, livelihoods, food security and resilience across three woredas | Benefits continue beyond donor support |

# Business and Service Delivery Model

The project will not distribute machines as private assets. Each power tiller will serve a defined cluster of nearby farmers and will be managed as a shared productive asset. Farmers will organize their plots into a service schedule so the machine can move efficiently from one farm to the next. This reduces travel and idle time and improves machine utilization.

The project uses a hybrid social-enterprise model: capital asset contribution + beneficiary cost recovery + controlled commercial hire services.

| Element | Proposed model |
| --- | --- |
| Capital assets | 15 × 24 HP power tillers; 5 per woreda |
| Ownership/custodianship | Legally recognized user groups under clear asset-use agreements |
| Primary users | Approximately 225-300 smallholders; 60% women-headed households and 40% men |
| Machine cluster | Approximately 15-20 organized users/user groups per power tiller, subject to field verification |
| Core service | Timely land preparation |
| Additional services | Rotavation, trailer transport and other productive uses where technically viable |
| Priority rule | Registered beneficiary needs are served first during peak periods |
| External customers | Neighboring farmers after priority beneficiary demand is secured |
| Pricing | Per hectare and/or hour, based on actual costs and reviewed annually |
| Revenue priority | Fuel → operator → routine maintenance → major-repair reserve → replacement reserve |
| Financial controls | Transparent records, banked revenues and at least two authorized signatories |
| Governance | Machine-level user committee plus woreda-level coordination |

# Mechanization Service

The core service will be timely land preparation. Depending on the selected model and implements, secondary tillage, rotavation and limited farm transport may also be provided where technically appropriate.

Machines will be operated by trained operators or trained farmers designated by the user group. Farmers will collectively govern and pay for the service; machine operation will be assigned to competent persons.

# Appropriateness of Power Tillers for Smallholder Farmers

The proposed use of two-wheel tractors (power tillers) is based on their potential suitability for the production conditions and farm characteristics of smallholder farmers in Chilga, Lay Armachiho and East Dembia Woredas. The technology provides an intermediate mechanization option between labour- and ox-drawn farming and the use of larger four-wheel tractors. Evidence from Ethiopia indicates that two-wheel tractors can improve the timeliness and efficiency of selected farm operations, while their relatively small size and multi-functionality create opportunities for shared access and service provision among smallholder farmers (Awoke et al., 2020; Daum et al., 2022).

Improved Timeliness and Field Capacity

Power tillers can substantially increase the speed and effective field capacity of land preparation and other farm operations compared with manual labour and traditional animal-powered methods. This is particularly important for smallholder farmers, for whom delays in land preparation and planting can affect the ability to complete operations within the appropriate agricultural window. Evidence from Ethiopia provides support for the potential timeliness advantage of two-wheel tractor technology. Awoke et al. (2020), in on-farm evaluations of two-wheel tractor-attached seeders in Ethiopia, reported substantial potential for reducing operating time compared with non-mechanized conventional practice. The study also found that improved uniformity and timing of planting were associated with higher wheat and maize yields under the conditions studied. These findings demonstrate the potential contribution of two-wheel tractor technology to timely and efficient farm operations, although actual performance will depend on the machinery, implement, soil condition, operator skills and farming system (Awoke et al., 2020).

Suitability for Smallholder and Clustered Farms

The relatively compact size and maneuverability of power tillers make them potentially appropriate for smallholder production systems where fields are relatively small, fragmented or difficult to access with larger agricultural machinery. This is particularly relevant to the proposed intervention because participating farmers will be organized into groups and encouraged to cluster geographically adjacent plots, enabling more efficient scheduling and utilization of each machine.

The proposed model, therefore, does not require each household to own a machine. Instead, a single power tiller will provide services to multiple organized user groups, allowing the cost and productive capacity of the machinery to be shared among participating farmers. This approach is consistent with the broader argument that mechanization options should be matched to the characteristics and needs of smallholder farming systems rather than applying a single mechanization model across different contexts (Daum et al., 2022).

Multipurpose Agricultural Use

Power tillers can be operated with different implements and attachments for activities beyond primary land preparation. Depending on the equipment available and the needs of participating farmers, potential applications include plowing, harrowing, rotavating, planting/seeding and transport using trailers. This multipurpose capacity creates opportunities to increase machine utilization and diversify the services provided to participating farmers over time.

Evidence from two-wheel tractor applications indicates that their multi-functionality can extend beyond primary tillage to activities such as planting, threshing and transportation, potentially improving machine utilization and the economic viability of mechanization services. However, the actual range of services will depend on the availability of appropriate attachments, technical capacity and demand from participating farmers. For the proposed project, the initial priority will remain timely land preparation and other services directly relevant to participating smallholder farmers. Additional uses can be introduced progressively where they are technically feasible and economically justified.

Potential for Cost and Labour Savings

Compared with continued dependence on manual labour or animal-powered operations, mechanized farm operations have the potential to reduce the time and labour required for selected agricultural activities. This can be particularly valuable where households face labour shortages or where peak-season demand for agricultural labour creates high costs and delays.

The Ethiopian evidence on two-wheel tractor-attached seeders demonstrates the potential for substantial reductions in operating time, while wider research on agricultural mechanization emphasizes the importance of selecting machinery that is economically appropriate to the scale and circumstances of smallholder farmers (Awoke et al., 2020; Daum et al., 2022). The economic benefit to participating farmers will nevertheless depend on actual fuel consumption, machine utilization, maintenance costs, operator costs, distance between farms and the service-fee structure established by the user groups. The project will therefore monitor operational costs and service utilization rather than assuming that mechanization will automatically generate higher household incomes.

Terrain and Farm Accessibility

The compact design of two-wheel tractors can provide an operational advantage where larger machinery may face difficulties accessing small or irregularly shaped plots. Their maneuverability can allow services to reach farms that may not be efficiently served by larger tractors, particularly where farmers' fields are relatively small or dispersed. In the proposed project, this potential advantage will be reinforced by the clustering of participating farmers and their landholdings. Geographic clustering is expected to reduce unnecessary movement between farms, improve machine scheduling and increase the productive use of each power tiller. At the same time, the project recognizes that power tiller performance is not uniform across all field conditions. Soil moisture, soil hardness, slope, traction, implement type and operator experience can affect field efficiency. The selection and use of the machinery will therefore need to take local conditions into account.

Technology Limitations and Risk Management

The project recognizes that power tillers are not without limitations. Their performance can be affected by soil condition, traction, implement selection and operator skill. In addition, access to trained mechanics, spare parts, fuel and reliable repair services may be limited in remote rural areas. Initial investment costs may also remain beyond the capacity of individual smallholder households. These constraints will be addressed through the project's community-based service model. Farmers will access the machinery collectively through organized user groups rather than through individual ownership. Operators will receive appropriate training, while user groups will establish arrangements for routine maintenance, repairs and maintenance reserves. The project will also facilitate linkages with local mechanics, spare-parts suppliers and relevant agricultural and technical service providers.

The experience of two-wheel tractor-based mechanization initiatives also suggests that access to finance, fuel, spare parts, infrastructure, technical skills and maintenance services can influence the sustainability of mechanization service provision. These considerations reinforce the importance of combining machinery provision with appropriate institutional and technical support. Accordingly, the project does not view the power tiller as a stand-alone technological solution. Its effectiveness will depend on the combination of appropriate machinery, organized users, clustered demand, trained operators, community contribution, user-financed operation and maintenance, and locally managed service arrangements.

# Project Investment and Cost Structure

The core investment is based on an assumed unit cost of ETB 200,000 per power tiller. The project will request 90% of the equipment cost, while communities contribute 10%. Operating costs are intentionally excluded from donor financing because beneficiaries will cover them.

| Budget item | Unit cost | Quantity | Amount |
| --- | --- | --- | --- |
| Power tillers | ETB 200,000 | 15 | ETB 3,000,000 |
| Community/users contribution | ETB 20,000 | 15 | ETB 300,000 |
| Project equipment contribution | ETB 180,000 | 15 | ETB 2,700,000 |
| Transport/delivery | Quotation | 15 | TBD |
| Commissioning/initial training | Quotation | 15 groups | TBD |

The final donor request will be finalized after supplier and transport quotations. Fuel, operator wages, servicing and repairs will be financed by beneficiary users.

# Community Contribution and Cost Sharing

| Item | Per machine (ETB) | 15 machines (ETB) |
| --- | --- | --- |
| Purchase cost | 200,000 | 3,000,000 |
| Community/users group contribution - 10% | 20,000 | 300,000 |
| Project contribution - 90% | 180,000 | 2,700,000 |

The users’ group contribution should be deposited or formally committed before procurement. The final price will be confirmed through supplier quotations.

# Operating and Maintenance Responsibility

All recurring costs will be paid by beneficiary users. The project will not be expected to finance routine operation after delivery.

| Cost | Responsible party |
| --- | --- |
| Fuel/diesel | Beneficiary users |
| Operator/labour cost | Beneficiary users |
| Lubricants and routine servicing | Beneficiary users |
| Routine spare parts | Beneficiary users |
| Breakdown repairs | Beneficiary users |
| Daily cleaning and care | Operator/user group |
| Secure storage | User group/community |
| Maintenance reserve | Built from user payments |

Each user group will establish a simple user-fee system based on actual fuel, labour, servicing and repair costs. A portion of payments will be retained as a maintenance reserve. Fees will be reviewed when costs change.

# Sustainability and Exit Strategy

The project is designed as a four-year institutional development and livelihood improvement initiative, rather than a permanent service-delivery arrangement. From the outset, responsibility for operating and maintaining the power tillers will rest with the organized user groups. Wogen Children and Mothers Support Association will serve as a facilitator, capacity builder and monitor, rather than as the permanent operator of the machines.

The project's sustainability will, therefore, depend on four mutually reinforcing elements:

- Community ownership and contribution: User groups contribute 10% of the machine cost as an ownership commitment.

- User-financed operation:  User groups cover fuel, operator costs, maintenance, repairs and other recurrent costs through an agreed service-fee and cost-recovery system.

- Local management capacity: User groups will develop transparent systems for scheduling, fee collection, financial records, maintenance and accountability.

- Local technical linkages:  User groups will establish relationships with local mechanics, spare-parts suppliers, agricultural extension services and other relevant service providers.

At project completion, the machines and associated management systems will remain under the agreed community/user-group arrangement, subject to applicable legal and asset-transfer requirements. The project will leave behind a functioning community-managed mechanization service rather than a dependency on Wogen or external financing.

# Procurement, Transport and Commissioning

Procurement will prioritize reliable, appropriate and locally serviceable power tillers rather than simply selecting the lowest-priced machine. Before purchase, the project will verify power, fuel consumption, field capacity, spare-parts availability, warranty, technical support and suitability for local conditions.

- Obtain competitive supplier quotations and confirm the final unit price.

- Procure 15 machines and essential implements required for the agreed service.

- Transport and deliver five machines to each target woreda.

- Inspect and test each machine after delivery.

- Register each machine and sign a user-group handover agreement.

- Provide operator orientation, safety and basic preventive-maintenance training before regular use.

Transport, delivery and commissioning costs will be budgeted separately from the machine purchase price and confirmed using quotations.

# Governance and Institutional Arrangements

| Actor | Main responsibility |
| --- | --- |
| User group/cluster | Ownership, scheduling, payments, oversight and accountability |
| User committee | Daily management, records, financial control and conflict resolution |
| Operator | Safe operation, daily checks, work records and fault reporting |
| Implementing organization | Procurement oversight, training, monitoring and donor reporting |
| Woreda agriculture office | Technical linkage and extension support |
| Local mechanic/service provider | Maintenance and repair support |

The machine will remain a community/group productive asset, not the private property of an individual. Written rules will define access, payment, scheduling, care and procedures when a member leaves.

# Gender and Inclusion Strategy

The project uses a deliberate gender-prioritization approach: 60% of direct users will be women-headed households and 40% will be men-headed households. Women will not be treated merely as recipients of a machine service; they will participate in decisions on scheduling, pricing, financial management, asset protection and future investment.

- Women-headed households receive priority in beneficiary selection consistent with the 60% target.

- Women are represented in each machine-level management committee.

- At least two women per machine cluster receive basic machine safety, maintenance and service-management orientation.

- Operator recruitment is competence-based, while women are actively encouraged to enter technical/operator training.

- Training and meetings are scheduled around household care and seasonal farming responsibilities.

- Verified hardship cases may use installment or harvest-time payment arrangements without undermining cost recovery.

- Women with disabilities or other constraints to physical machine operation can participate through governance, farming and service-use arrangements.

# Implementation Schedule

|  |  | Activities |  |  |
| --- | --- | --- | --- | --- |
| Year I (2027) | Year II (2028) |  | Year III (2029) | IV (2030) |
| Mobilize communities | Monitor service delivery |  | Assess machine utilization | Assess sustainability |
| Select beneficiaries | Support groups to establish effective scheduling |  | Identify under-utilization or management problems | Strengthen independent community management |
| Facilitate land clustering | Monitor cost recover |  | Strengthen financial/business management | Conduct final evaluation |
| Establish user groups | Monitor maintenance |  | Improve service pricing and cost recovery | Document the model |
| Procure equipment | Facilitate solutions to operational problem |  | Strengthen user-group leadership | Develop a replication/scale-up strategy |
| Coordinate delivery | Strengthen women's participation |  | Document lessons | Gradually withdraw direct project support |
| Organize commissioning | Connect groups with mechanics and agricultural extension services |  |  |  |
| Facilitate training |  |  |  |  |

# Results Framework

| Result | Indicator | 4-year target |
| --- | --- | --- |
| Machines operational | Power tillers delivered and functional | 15 |
| Geographic coverage | Woredas served | 3 |
| Beneficiary access | Smallholders using services | 225-300 |
| Women's participation | Women-headed households | ≥60% |
| Timely service | Participating farmers receiving service in agreed window | ≥80% annually |
| Cost recovery | Routine operating costs covered by users | 100% |
| Capacity | Operators/user committees trained | All 15 machine groups |

# Monitoring and Learning

Each machine will keep a simple logbook recording farmers/groups served, hectares covered, fuel used, operator payments, breakdowns and repairs. Quarterly and annual reviews will examine machine use, costs, women's participation, user satisfaction and maintenance funds.

- Farmers and hectares served.

- Share of women-headed households served.

- Cost per hectare and payments collected.

- Fuel consumption and machine utilization.

- Repair frequency and cost.

- User satisfaction and complaints.

- Maintenance reserve balance.

# Key Risks and Mitigation

| Risk | Mitigation |
| --- | --- |
| Breakdown during peak season | Preventive maintenance, spare parts and local mechanic support |
| Fuel price increases | Regular review of user fees based on actual costs |
| Low machine utilization | Geographical clustering and advance service scheduling |
| Scheduling disputes | Written rules and transparent schedules |
| Poor maintenance | Maintenance contribution included in user fees and regular records |
| Elite capture | Transparent selection and grievance mechanism |
| Theft/damage | Secure storage, asset register and clear custody |
| Women's participation falls below target | 60% target monitored and women represented in committees |